## CRM Sprint Items
# | Item | Description | Status
1 | CR-069 | WhatsApp templates with dynamic URL buttons (e.g. final_bill) had buttons invisible throughout the CRM — Map Variables dialog, preview bubbles, campaign wizard, and send payload all ignored them. Full button support wired end-to-end. | ✅ QA PASS · Owner smoke pending
2 | CR-076 | Customer Lifecycle Re-engage feature. Adds bulk 'Re-engage Churned/At-Risk (N)' CTA on Lifecycle page, inline direct-send modal, lifecycle_stage filter in Audiences, and Campaign Wizard pre-fill from lifecycle page. | ✅ QA PASS · Owner smoke pending
3 | CR-077 | 7 hardcoded thresholds (lifecycle days, campaign daily limit, VIP score bands, churn thresholds) made configurable per-tenant via loyalty_settings. Defaults match old hardcoded values — zero behavior change on upgrade. | ✅ QA PASS 22/22 · Owner smoke pending
4 | BUG-011 | Campaign History showed Delivered/Read as always 0. Root cause: campaign_runs.total_delivered/total_read was never incremented anywhere. Fix: read-time aggregation from whatsapp_message_logs at the runs endpoint. | ✅ QA PASS
5 | BUG-012 | Message Status page ignored deep-link filter (?campaign_id=X). Root cause: mount effect triggered an unfiltered fetch that raced and overwrote the filtered result. Fix: lazy filter init + last-request-wins guard. | ✅ QA PASS
6 | CR-061 | CRM template authoring gate removed — all tenants can now build templates. Previously restricted via env allowlist. Frontend visibility flag (crm_templates_enabled) still works; backend 403 gate commented out. | ✅ QA PASS 13/13
7 | CRM-2 | Document upload endpoint POST /api/pos/customers/{id}/documents returned 422 instead of 400 when the file was absent. Root cause: FastAPI validation fired before function body. Fixed by making file Optional + explicit null-guard. | ✅ QA PASS
8 | CR-075 | Hotel guest document migration. Extends existing customer sync to pull booking_documents from POS — downloads images and re-uploads to S3 following CR-072 naming convention. Idempotent, runs every sync. | ✅ QA PASS 10/10
9 | CR-067 | Template deletion lifecycle. Delete from CRM now cascades to Meta (with warning modal). AuthKey sync auto-removes local records when template is gone. Check-status detects externally deleted templates. | 🔵 Planning Approved
10 | CR-068 | Standalone 'Validate' button in Template Builder. Runs V1-V23 compliance checks instantly with zero API calls — works for tenants without Meta WABA configured. Frontend-only, ~35 LOC. | 🔵 Planning Approved