## Bug Registry
✅ QA PASS — Owner Smoke Pending
Bug ID | Title | Description | Status | QA Result | Last Touched
BUG-020 | Unknown name in WhatsApp → Guest | 'Unknown' customer name was sent in WhatsApp templates. resolve_variable() now treats 'Unknown' as blank and returns 'Guest' instead. | ✅ FIXED | 26/26 PASS (iter_1) | 2026-08-04
BUG-021 | POS order never updates customer name/email | When a POS order arrived for an existing customer, name & email were never refreshed. customer_update_set now writes name and email from every real POS order. | ✅ FIXED | 26/26 PASS (iter_1) | 2026-08-04
BUG-022 | Migration re-sync overwrites manually-edited names | Running migration sync reset CRM-edited names back to 'Unknown' from MyGenie POS. _is_placeholder_name() guard added — re-sync skips name if CRM already has a real value. | ✅ FIXED | 26/26 PASS (iter_1) | 2026-08-04
BUG-023 | weasyprint missing → einvoice_token always empty | weasyprint was absent from requirements.txt; production deploys had no PDF library. einvoice_token was always empty. Added to requirements; PDF now generated after DB insert. | ✅ FIXED | 26/26 PASS (iter_1) | 2026-08-04
BUG-013 | Bulk import 345 rows → Cloudflare 502 timeout | Sequential update_one per row (×345 × ~242ms remote Mongo RTT) took 83–167s > proxy limit. Replaced with single bulk_write() — import now completes in under 2 seconds. | ✅ FIXED | 21/21 PASS (iter_18) | 2026-07-14
BUG-014 | WhatsApp Opt-in column silently discarded in import | Import CSV's 'WhatsApp Opt-in' column was ignored; new customers hardcoded to opt_in=False. Now parses Yes/No/blank correctly; new customers default to opt_in=True. | ✅ FIXED | 21/21 PASS (iter_18) | 2026-07-14
BUG-010 | Media-header template blocked in Campaign Wizard | Templates with media headers approved on Meta showed 'no uploaded file' block in wizard. create_meta_template() now persists send_media_url + header_handle on direct submit. | ✅ FIXED | 7/7 PASS (iter_10) | 2026-07-11
CRM-2 | Document upload returns 422 instead of 400 | POST /api/pos/customers/{id}/documents with no file returned 422 (FastAPI validation). Changed to Optional[UploadFile] = File(None) + explicit 400 null-guard in function body. | ✅ FIXED | Self-test PASS | 2026-08-05
✅ QA PASS — Closed
Bug ID | Title | Description | Status | QA Result | Last Touched
BUG-019 | Backend V11-V20 validation ran after WABA check | Tenants without WABA got '503 WABA not configured' instead of a compliance error. V11-V20 validation block moved BEFORE the WABA guard in create_meta_template(). | ✅ FIXED | 20/20 PASS (iter_2) | 2026-07-17
BUG-018 | Stale comment in whatsapp.py validation block | Comment described 'V11-V15 only' but scope had expanded to V11-V20 in CR-066. Comment updated to reflect current V11-V20 scope. Zero logic change. | ✅ FIXED | 20/20 PASS (iter_2) | 2026-07-17
BUG-017 | Emoji count regex mismatch frontend vs backend | Frontend counted 17 emoji, backend counted 8 for the same string — split enforcement. Backend regex updated to match frontend's Unicode property escape approach. | ✅ FIXED | 20/20 PASS (iter_2) | 2026-07-17
BUG-016 | Orphan marker regex used unsupported JS lookbehind | (?<!\w)_ regex caused issues in certain browser/Node.js engines during preview. Replaced with a compatible regex alternative — same match, no lookbehind syntax. | ✅ FIXED | 20/20 PASS (iter_2) | 2026-07-17
BUG-015 | V19/V21/V22 hard-blocked valid Meta-approved templates | Char-limit, category-mismatch, ALL-CAPS checks were blocking templates Meta would approve. Moved V19/V21/V22 from errors[] to warnings[] — non-blocking yellow toast on submit. | ✅ FIXED | 20/20 PASS (iter_2) | 2026-07-17
BUG-009 | Details button on Campaign History did nothing | Button had no onClick handler — clicking produced no reaction, no navigation. Now navigates to /message-status?campaign_id=X&run_id=Y with a filtered view banner. | ✅ FIXED | 38/38 PASS (iter_3) | 2026-07-03
BUG-008 | CRM token pushed to POS on every login | Token was pushed unconditionally; POS returned 409 on every subsequent login. Push now gated by crm_token_registered_with_pos flag; regenerate also pushes new key. | ✅ FIXED | 9/9 PASS (iter_3) | 2026-06-18
BUG-007 | Template preview showed literal \n instead of line breaks | AuthKey returns temp_body with escaped \n characters; CSS whitespace-pre-wrap didn't render them. Fixed with .replace(/\\n/g, '\n') at 6 preview render points across 3 pages. | ✅ FIXED | QA PASS | 2026-06-17
BUG-005 + 006 | Campaign filter broken + messages logged with wrong ID | BUG-005: filter dropdown showed segments not campaigns. BUG-006: messages stored run_id not campaign_id. Both fixed together — filter queries campaigns collection; logs now store correct campaign_id. | ✅ FIXED | QA PASS | 2026-06-17
BUG-001–004 | Campaign wizard — menu_pick, event vars, template filter, test-send | menu_pick_resolved never set; event vars empty in broadcasts; rejected templates visible; test-sends hidden. All 4 fixed individually in CampaignWizardPage.jsx and routers/campaigns.py. | ✅ FIXED | QA PASS | 2026-06-17
⬜ Implemented — Testing Agent Not Yet Run
Bug ID | Title | Description | Status | QA Result | Last Touched
BUG-011 | Campaign History Delivered/Read always 0 | _augment_run_stats() reads whatsapp_message_logs at query time — computes real delivered/read counts. No backfill, no webhook change — pure read-time fix. Test file: test_bug011_run_stats.py. | ⬜ IMPLEMENTED | Test file exists | 2026-07-12
BUG-012 | View Messages deep-link shows all messages despite filter | Mount-time double-fetch race: unfiltered response resolved last, overwriting filtered results. Lazy filter init from searchParams + last-request-wins AbortController guard added. | ⬜ IMPLEMENTED | No test file yet | 2026-07-12
🔴 Open — No Fix Applied
Bug ID | Title | Description | Status | QA Result | Last Touched
BUG-024 | Bill button in WhatsApp opens 404 | 3 templates submitted to Meta with button URL missing /api/invoices/ segment — URL locked in approval. Options: (A) resubmit templates to Meta (B) Nginx redirect (C) React route. Owner decision pending. | 🔴 OPEN | No fix yet | 2026-08-04